## Sheet1
ID | Target Date | Day Category | Module | Task Name | Original Status | Actual Implementation Status | Description
1 | 15-Jun-26 | Day 1 | Project Init | Repo & Folder Structure | ? Done | Completed | Create Git repository with branching strategy (main/dev/feature). Set up project folder structure with separate folders: /frontend, /backend, /lead-discovery, /campaigns, /ai-calling, /crm, /analytics, /settings.
2 | 15-Jun-26 | Day 1 | Project Init | React Frontend Scaffold | ? Done | Completed | Initialize React app (Vite/CRA), install core dependencies (React Router, Axios, TailwindCSS or chosen UI lib), configure ESLint, Prettier, and commit base layout component.
3 | 15-Jun-26 | Day 1 | Project Init | FastAPI Backend Scaffold | ? Done | Partially Done (Used MongoDB instead) | Initialize FastAPI project, install dependencies (SQLAlchemy, Alembic, Pydantic, python-dotenv, uvicorn), create /api/v1 router structure with placeholder endpoints for each module.
4 | 15-Jun-26 | Day 1 | Project Init | PostgreSQL Database Setup | ? Done | Partially Done (Used MongoDB instead) | Provision PostgreSQL instance (local Docker), create development database, configure connection string in .env, verify Alembic can connect and run migrations.
5 | 15-Jun-26 | Day 1 | Project Init | Docker Configuration | ? Done | Not Started (Missing docker-compose.yml) | Write docker-compose.yml with services for frontend (Node), backend (Python), PostgreSQL, and optional Redis for queue. Set up .env.example with all required environment variable keys.
6 | 15-Jun-26 | Day 1 | Project Init | Coding Standards & CI Setup | ? Done | Completed | Document coding standards (naming conventions, file structure, commit message format). Set up GitHub Actions or equivalent CI pipeline to run linting and tests on every PR.
7 | 16-Jun-26 | Day 2 | Auth | User Registration API | ? Done | Completed | POST /api/v1/auth/register � validate email uniqueness, hash password (bcrypt), create user record with default role='user', return 201 with user_id.
8 | 16-Jun-26 | Day 2 | Auth | Login & JWT Token API | ? Done | Completed (Route /login) | POST /api/v1/auth/login � verify credentials, issue access token (15min) + refresh token (7 days) as HTTP-only cookies. Token payload includes user_id and role.
9 | 16-Jun-26 | Day 2 | Auth | JWT Middleware & Protected Routes | ? Done | Completed (PrivateRoute.tsx) | Create FastAPI dependency that validates access token on protected endpoints. Create React PrivateRoute component that redirects unauthenticated users to /login.
10 | 16-Jun-26 | Day 2 | Auth | Role Management | ? Done | Partially Done | Define roles: 'user' and 'admin'. Add role-check decorator/dependency for admin-only endpoints. Admin users can view all users; regular users see only their own data.
11 | 16-Jun-26 | Day 2 | Auth | Forgot Password & Reset Flow | ? Done | Completed (Route /forgot-password) | POST /auth/forgot-password � generate time-limited reset token, send email link. POST /auth/reset-password � validate token, update hashed password, invalidate token.
12 | 16-Jun-26 | Day 2 | Auth | Frontend Auth UI (Login / Register) | ? Done | Completed (Route /register) | Build /login and /register pages with form validation, error display, and redirect to dashboard on success. Store tokens and handle token refresh.
13 | 17-Jun-26 | Day 3 | Dashboard | Sidebar Navigation | ? Done | Completed (Dashboard.tsx exists) | Build collapsible sidebar with links to: Get Data, Campaigns, CRM, Analytics, Settings, Admin (admin-only). Active state highlighting. Logo / brand area at top.
14 | 17-Jun-26 | Day 3 | Dashboard | Header & Profile Section | ? Done | Completed (Dashboard.tsx exists) | Build top header bar with page title, user avatar/initials, notification bell icon (placeholder), and profile dropdown with 'My Account' and 'Logout' options.
15 | 17-Jun-26 | Day 3 | Dashboard | Dashboard Stats Cards | ? Done | Completed (Dashboard.tsx exists) | Build 4 summary cards on the /dashboard home: Total Leads, Active Campaigns, Calls Made Today, Meetings Booked. Cards show placeholder values; will connect to live API later.
16 | 17-Jun-26 | Day 3 | Dashboard | Responsive Layout & Routing | ? Done | Completed (Dashboard.tsx exists) | Ensure layout adapts to desktop (sidebar open), tablet (sidebar collapsed), and mobile (hamburger menu). Set up React Router routes for all pages with correct layouts.
17 | 18-Jun-26 | Day 4 | Database | Core Schema � Users & Auth | ? Done | Partially Done (Using MongoDB, schema not strictly defined via Alembic) | Create Alembic migration for: users (id, email, hashed_password, role, created_at), refresh_tokens (token_hash, user_id, expires_at, revoked).
18 | 18-Jun-26 | Day 4 | Database | Schema � Connected Accounts | ? Done | Partially Done (Using MongoDB, schema not strictly defined via Alembic) | Create connected_accounts table: (id, user_id FK, integration_name ENUM, credentials_encrypted TEXT, status ENUM[connected/disconnected/expired], connected_at, updated_at).
19 | 18-Jun-26 | Day 4 | Database | Schema � Leads | ? Done | Partially Done (Using MongoDB, schema not strictly defined via Alembic) | Create leads table: (id, user_id FK, name, company, designation, email, phone, linkedin_url, website, location, lead_score, source ENUM[scraped/apollo/uploaded], tags[], status, created_at, updated_at).
20 | 18-Jun-26 | Day 4 | Database | Schema � Campaigns, Calls, Emails, LinkedIn | ? To Do | Partially Done (Using MongoDB, schema not strictly defined via Alembic) | Create campaigns (id, user_id, channel ENUM, niche ENUM, status, vapi_assistant_id, created_at), calls (id, campaign_id, lead_id, recording_url, transcript, outcome, duration, called_at), emails (id, campaign_id, lead_id, subject, body, reply_body, status, sent_at), linkedin_messages (id, campaign_id, lead_id, message, status, sent_at).
21 | 18-Jun-26 | Day 4 | Database | Schema � Vapi Assistants, Recordings, Transcripts, Analytics | ? To Do | Partially Done (Using MongoDB, schema not strictly defined via Alembic) | Create vapi_assistants (id, campaign_id FK, vapi_id, config_json, status ENUM[active/archived]), recordings (id, call_id, storage_url, duration), transcripts (id, call_id, text, created_at), analytics_events (id, user_id, campaign_id, event_type, event_data JSON, created_at).
22 | 19-Jun-26 | Day 5 | Settings | Connected Accounts UI Page | ? Done | Completed (Integrations.tsx) | Build Settings > Connected Accounts page listing all 9 integrations: Twilio, Email (Gmail/Outlook), Calendar, Google Maps, Apify, Uniple, Apollo.io, Hunter.io, LinkedIn. Each shows integration name, logo, description, status badge (Connected/Not Connected/Expired), and a Connect/Disconnect button.
23 | 19-Jun-26 | Day 5 | Settings | API Key Entry & Encryption | ? Done | Completed | For API-key integrations (Twilio, Maps, Apify, Uniple, Apollo.io, Hunter.io): build modal with secure input field, call POST /api/v1/settings/integrations/{name} to save. Backend encrypts value (AES-256) before storing in connected_accounts table.
24 | 19-Jun-26 | Day 5 | Settings | OAuth Flow � Email & Calendar | ? Done | Completed (Route /google/login, /email/connect) | Implement OAuth 2.0 authorization code flow for Gmail/Outlook and Google Calendar. Backend exchanges code for access+refresh tokens and stores encrypted. Handle token refresh automatically.
25 | 19-Jun-26 | Day 5 | Settings | OAuth Flow � LinkedIn | ? To Do | Completed (Route /linkedin/login) | Implement LinkedIn OAuth 2.0 for the LinkedIn integration. Request required scopes (r_liteprofile, w_member_social). Store tokens encrypted per user.
26 | 19-Jun-26 | Day 5 | Settings | Integration Status Gating | ? To Do | Partially Done | Implement middleware/frontend logic that checks required integration status before allowing a dependent action. E.g., if user tries to start Call Campaign without Twilio connected, show a warning banner linking to Settings.
27 | 20-Jun-26 | Day 6 | Get Data | Natural Language Search UI | ? Done | Completed (Discovery.tsx, /search) | Build Get Data page with: large search input (placeholder: 'Find 50 AI founders with 5+ employees in Hyderabad'), search history list (last 10 queries), quick-filter chips for industry/location, and a results panel that will stream leads.
28 | 22-Jun-26 | Day 7 | Get Data | Query Understanding Engine (NLP Parser) | ? Done | Completed (/parse) | Build AI-powered query parser (call Claude/GPT API or custom NLP) that takes natural language input and returns structured JSON: {industry, designation, years_exp, location, company_size, employee_count, limit}. Cache parsed results.
29 | 23-Jun-26 | Day 8 | Get Data | Apollo.io Integration Setup | ? To Do | Not Started (No Apollo integration found) | Integrate Apollo.io API using user's stored API key. Build ApolloService with methods: search_people(filters) and get_person(id). Handle rate limits and errors gracefully.
30 | 24-Jun-26 | Day 9 | Get Data | Apollo Lead Extraction & Mapping | ? To Do | Not Started (No Apollo integration found) | Parse Apollo API response and map to internal lead schema: name, company, designation, linkedin_url, email, company_details (size, industry, website). Handle missing fields gracefully.
31 | 25-Jun-26 | Day 10 | Get Data | Hunter.io Integration � Email Enrichment | ? To Do | Not Started (No Hunter integration found) | Integrate Hunter.io API using user's stored API key. For leads missing email, call Hunter domain-search or email-finder API to attempt enrichment. Append result to lead profile.
32 | 26-Jun-26 | Day 11 | Get Data | Google Maps / Places Integration | ? Done | Completed (Route /google, test_google.py) | Integrate Google Places API using user's connected Maps API key. Search for local businesses by query + location. Extract business name, phone, website, address, rating. Map to lead schema.
33 | 27-Jun-26 | Day 12 | Get Data | Website Scraper � Apify / Uniple | ? To Do | Not Started | Build scraping service that takes a company website URL, calls Apify or Uniple API (using user's stored key), and extracts: phone numbers, emails, social links, contact page info. Return structured result.
46 | 10-Jul-26 | Day 23 | Campaigns | Script Editor UI | ? To Do | Completed (Templates.tsx) | Display generated script in a rich text editor (TipTap or Quill). Allow user to edit any section. 'Regenerate' button to get a new AI version. 'Save & Continue' stores final script.
47 | 11-Jul-26 | Day 24 | Call Campaign | Voice Selection UI | ? To Do | Not Started (No Vapi integration found) | For Call campaigns: build voice configuration step. Options: voice type (male/female/neutral), language (EN/HI/other), accent, speaking speed, tone. Selections stored in campaign.voice_config.
48 | 11-Jul-26 | Day 24 | Call Campaign | Vapi Assistant Provisioning | ? To Do | Not Started (No Vapi integration found) | Backend service: on call campaign creation, call Vapi API to create a new assistant using the generated prompt + voice config. Store returned vapi_assistant_id in vapi_assistants table. One assistant per campaign � do not reuse across campaigns.
49 | 13-Jul-26 | Day 25 | Call Campaign | Campaign Builder � Final Review & Launch | ? To Do | Not Started (No Vapi integration found) | Campaign summary screen showing: channel, niche, lead list (count), script excerpt, voice config, Vapi assistant ID, launch mode (Immediate / Scheduled). 'Launch Campaign' button triggers campaign activation.
50 | 14-Jul-26 | Day 26 | Call Campaign | Calling Queue Manager | ? To Do | Not Started (No Vapi integration found) | Build queue system (Redis/Celery or similar) that takes campaign lead list and dispatches calls to Vapi via Twilio. Implement rate limiting (max N concurrent calls), retry logic (up to 3 attempts per lead), and pause/resume controls.
51 | 15-Jul-26 | Day 27 | Call Campaign | Twilio + Vapi Integration | ? To Do | Not Started (No Vapi integration found) | Wire Vapi assistant calls through user's connected Twilio account. Calls should originate from the user's Twilio phone number. Handle webhooks from Twilio for call status events (initiated, answered, completed, failed).
52 | 16-Jul-26 | Day 28 | Call Campaign | Call Scheduling System | ? To Do | Not Started (No Vapi integration found) | Allow 'Schedule for Later' option: datetime picker with timezone selection. Store scheduled_at on campaign. Background scheduler (APScheduler or Celery Beat) triggers queue at specified time.
53 | 17-Jul-26 | Day 29 | Call Campaign | Call Recording Storage | ? To Do | Not Started (No Vapi integration found) | Capture recording URL from Vapi/Twilio webhook, download to secure storage (S3 or equivalent), store storage_url in recordings table mapped to call_id and campaign_id. Recordings accessible only to the campaign owner.
54 | 18-Jul-26 | Day 30 | Call Campaign | Transcript Processing & Storage | ? To Do | Not Started (No Vapi integration found) | Get transcript from Vapi webhook or poll Vapi transcript API post-call. Parse transcript into structured format (speaker turns). Store in transcripts table. Display transcript in call detail view.
55 | 20-Jul-26 | Day 31A | Email Campaign | Email Campaign Sending Engine | ? Done | Completed (Route /email/send) | Backend service: iterate over campaign lead list, personalize email template per lead (merge first name, company name into template), send via connected email account (Gmail/Outlook OAuth). Respect send-rate limits (e.g., max 50/hour for Gmail).
56 | 20-Jul-26 | Day 31A | Email Campaign | In-Platform Inbox View | ? Done | Completed (Inbox.tsx, /email/messages) | Build Inbox page that loads emails from the user's connected email account (via Gmail/Outlook API). Display received emails with sender, subject, date, preview. Filter to show only replies to campaign emails.
57 | 20-Jul-26 | Day 31A | Email Campaign | Reply-to-Lead Association | ? Done | Partially Done | When a reply arrives in the connected inbox, match it to the originating lead and campaign by Message-ID or sender email. Update emails table with reply_body and change lead status based on content.
58 | 21-Jul-26 | Day 32A | LinkedIn | LinkedIn Outreach Engine | ? To Do | Completed (/linkedin/publish) | Build LinkedIn campaign engine that sends connection requests or InMail messages (via user's connected LinkedIn OAuth) using the generated niche template. Personalize per lead's name and company.
59 | 21-Jul-26 | Day 32A | LinkedIn | LinkedIn Engagement Tracking & Rate Limiting | ? To Do | Partially Done | Poll LinkedIn API for connection acceptance and message replies. Update CRM lead status on engagement. Enforce LinkedIn rate limits (e.g., max 100 connection requests/week) per connected account to reduce restriction risk.
60 | 21-Jul-26 | Day 32 | CRM | CRM Lead Detail View | ? To Do | Completed (Leads.tsx, Contacts.tsx) | Build CRM lead detail page showing: lead profile (all fields), cross-channel communication timeline (calls, emails, LinkedIn messages in chronological order), campaign associations, current status, and follow-up tasks.
61 | 21-Jul-26 | Day 32 | CRM | Lead Status Automation Engine | ? To Do | Not Started | Implement auto-classification service: analyze call transcripts (keyword matching + sentiment or LLM), email reply content, and LinkedIn responses to classify lead as: Interested / Not Interested / Callback Requested / Meeting Booked / No Answer / Closed. Update lead.status automatically.
62 | 21-Jul-26 | Day 32 | CRM | Post-Campaign Auto-Routing | ? To Do | Not Started | Implement post-campaign workflow: Interested/Meeting Booked ? hot lead queue + CRM task. No Answer/Callback ? retry queue (max 3 attempts, cooldown). Not Interested ? suppressed. Meeting Booked + Calendar connected ? auto-create calendar event.
63 | 21-Jul-26 | Day 32 | CRM | Follow-Up Auto-Enrollment | ? To Do | Not Started | Leads classified as Interested or Callback Requested are automatically enrolled into a Follow-up niche campaign on a configurable alternate channel (e.g., call lead ? try email next). Allow user to configure this preference in Settings.
64 | 22-Jul-26 | Day 33 | Analytics | Analytics Dashboard | ? To Do | Completed (Analytics.tsx) | Build analytics page with charts: (1) Call volume over time (line), (2) Conversion rate by campaign (bar), (3) Lead status breakdown (pie/donut), (4) Channel performance comparison (Call vs Email vs LinkedIn). All charts filterable by date range and campaign.
65 | 23-Jul-26 | Day 34 | Reporting | Campaign Performance Report (PDF/Excel) | ? To Do | Not Started | Generate downloadable report per campaign: total leads contacted, connected/answered rate, outcome breakdown, conversion rate, cost per meeting booked (if Twilio cost data available). Export as PDF (styled) and Excel (raw data).
66 | 24-Jul-26 | Day 35 | Notifications | Notifications System | ? To Do | Not Started | Build notification service: in-app notifications (bell icon) + optional email notifications for: Campaign completed, Meeting booked, New email reply received, Lead status changed to Interested. Mark-as-read functionality.
67 | 24-Jul-26 | Day 35 | Reporting | Re-Engagement Scheduling | ? To Do | Not Started | Not Interested / Closed leads enter 90-day suppression window stored in lead.reengagement_eligible_at. Background job runs daily to move eligible leads back to 'Ready to Contact' status and optionally notify the user.
68 | 25-Jul-26 | Day 36 | LinkedIn Campaign | LinkedIn Campaign Database Schema | ? Done | Completed (MongoDB used) | Design database tables for LinkedIn posts, campaigns, templates, images, schedules, and analytics. Create relationships between campaigns, posts, and generated images. Set up migrations.
69 | 25-Jul-26 | Day 36 | LinkedIn Campaign | LinkedIn API Integration Setup | ? Done | Completed (/linkedin/login) | Set up LinkedIn API OAuth2 authentication flow. Configure app credentials, permissions (w_member_social, r_liteprofile). Create token management service for refresh tokens.
70 | 26-Jul-26 | Day 37 | LinkedIn Campaign | AI Image Generation Service | ? Done | Partially Done | Integrate AI image generation API (DALL-E 3 / Stable Diffusion). Create image generation service with prompt engineering for professional LinkedIn-style images. Support multiple aspect ratios (1:1, 1.91:1, 4:5).
71 | 26-Jul-26 | Day 37 | LinkedIn Campaign | Image Template System | ? Done | Partially Done | Create branded image template system. Support company logo overlay, text overlays, brand colors, and preset layouts (announcement, quote, infographic, carousel frames).
72 | 27-Jul-26 | Day 38 | LinkedIn Campaign | AI Post Content Generator | ? Done | Partially Done | Build AI-powered post content generator using LLM. Support different post types (thought leadership, product announcement, company update, engagement post). Include hashtag suggestions and emoji recommendations.
73 | 27-Jul-26 | Day 38 | LinkedIn Campaign | Post Editor UI | ? Done | Partially Done | Create rich post editor with real-time preview. Support text formatting, image attachment/preview, carousel builder, poll creation, and character count with optimal length indicator.
74 | 28-Jul-26 | Day 39 | LinkedIn Campaign | Campaign Builder & Management | ? Done | Partially Done | Build campaign creation wizard: define campaign name, goals, target audience persona, content themes, posting frequency. Create campaign dashboard with post calendar view.
75 | 28-Jul-26 | Day 39 | LinkedIn Campaign | Post Scheduling System | ? Done | Partially Done | Implement post scheduling with timezone support. Create scheduling queue with best-time recommendations based on audience insights. Support recurring posts and bulk scheduling.
76 | 29-Jul-26 | Day 40 | LinkedIn Campaign | LinkedIn Publishing Service | ? Done | Partially Done | Build publishing service to post content via LinkedIn API. Handle image uploads, text posts, and multi-image carousels. Implement retry logic and error handling for API failures.
77 | 29-Jul-26 | Day 40 | LinkedIn Campaign | Post Analytics Dashboard | ? Done | Partially Done | Create analytics dashboard pulling data from LinkedIn API (impressions, clicks, engagement rate, comments, shares). Show performance by post type, time of day, and content theme.
78 | 31-Jul-26 | Day 41 | LinkedIn Campaign | Content Library & Reusability | ? Done | Partially Done | Build content library to save drafts, templates, and high-performing posts. Implement AI-powered content repurposing (turn blog to LinkedIn post, refresh old posts).
79 | 31-Jul-26 | Day 41 | LinkedIn Campaign | LinkedIn Module Testing & Integration | ? To Do | Partially Done | End-to-end testing of LinkedIn module: OAuth flow, image generation, post creation, scheduling, publishing, and analytics. Fix bugs and optimize performance.
80 | 1-Aug-26 | Day 42 | Admin | Admin Dashboard & User Management | ? To Do | Not Started | Build admin-only /admin section: user list (name, email, role, created date, status), ability to deactivate/reactivate users, view per-user campaign and lead counts.
81 | 1-Aug-26 | Day 42 | Admin | API Key & Integration Monitoring | ? To Do | Not Started | Admin view showing all users' integration connection statuses (not the keys themselves). Flag users with expired connections. Allow admin to send 'reconnect your account' notification.
82 | 01-Aug-26 | Day 42 | Admin | Vapi Assistant Inventory | ? To Do | Not Started | Admin view of all provisioned Vapi assistants across all users: assistant ID, campaign name, user, status (active/archived), created date. Total count visible. Allows admin to archive active assistants manually.
83 | 02-Aug-26 | Day 43 | Security | API Security � Rate Limiting & Auth | ? To Do | Not Started | Implement: (1) Rate limiting per IP and per user token (using slowapi or Redis), (2) CORS configuration for allowed origins, (3) HTTPS enforcement, (4) Input validation on all API endpoints (Pydantic), (5) SQL injection protection via ORM.
84 | 02-Aug-26 | Day 43 | Security | RBAC & Audit Logging | ? To Do | Not Started | Role-based access control verified on all sensitive endpoints. Create audit_log table (user_id, action, entity_type, entity_id, ip_address, timestamp). Log all write actions (create, update, delete) and auth events (login, failed login).
85 | 03-Aug-26 | Day 44 | QA | Unit & Integration Tests | ? To Do | Not Started | Write unit tests for: query parser, lead enrichment merge logic, Vapi provisioning service, auto-classification engine. Write integration tests for: auth flow, full Get Data pipeline, call campaign launch.
86 | 03-Aug-26 | Day 44 | QA | End-to-End User Flow Testing | ? To Do | Not Started | Manually test full E2E flow: (1) Register/login, (2) Connect Twilio/Email/Apollo, (3) Run Get Data query, (4) Create Call campaign, (5) Launch campaign, (6) Review calls + CRM, (7) Download report. Document all bugs.
87 | 03-Aug-26 | Day 44 | QA | Bug Fixes & Regression | ? To Do | Not Started | Fix all High and Medium priority bugs found during E2E testing. Re-run test suite after fixes. Ensure no regressions introduced.
88 | 04-Aug-26 | Day 45 | Deploy | Production Environment Setup | ? To Do | Not Started | Provision production server/cloud (VPS or cloud provider). Configure environment variables, SSL certificate, domain, reverse proxy (Nginx). Set up managed PostgreSQL and Redis. Configure S3 bucket for recordings.
89 | 04-Aug-26 | Day 45 | Deploy | CI/CD Pipeline & Deployment | ? To Do | Not Started | Configure automated deployment pipeline: on merge to main ? run tests ? build Docker images ? push to registry ? deploy to production. Set up rollback mechanism.
90 | 04-Aug-26 | Day 45 | Deploy | Monitoring & Alerting Setup | ? To Do | Not Started | Set up application monitoring (Sentry for errors, or similar). Configure uptime monitoring. Set up alerts for: backend errors >1%/min, DB connection failures, queue backlog >500 items.
91 | 05-Aug-26 | Day 46 | Documentation | Technical Documentation | ? To Do | Not Started | Write: (1) System architecture overview with diagrams, (2) Database schema documentation with ERD, (3) Environment setup guide for new developers, (4) Module-by-module codebase walkthrough.
92 | 05-Aug-26 | Day 46 | Documentation | API Documentation | ? To Do | Not Started | Document all backend API endpoints using FastAPI auto-docs (Swagger/OpenAPI) + write a supplementary API guide covering: authentication flow, integration setup, campaign lifecycle, webhook payloads for Vapi/Twilio.
93 | 05-Aug-26 | Day 46 | Documentation | Deployment Guide & Handover | ? To Do | Not Started | Write production deployment guide covering: environment variable reference, Docker commands, DB migration steps, SSL setup, secrets management. Record a 30-min walkthrough video of the live system.
Date | Day | Task | Detailed Description | Deliverables |  | Not Started
15-Jun-26 | Day 1 | Project Initialization | Setup React frontend, FastAPI backend, PostgreSQL database, Git repository, Docker configuration, environment variables, project folder structure and coding standards. Create separate folders for Lead Discovery, Campaigns, AI Calling, CRM and Analytics modules. | Running frontend and backend connected to database |  | Partially Done (Using MongoDB, schema not strictly defined via Alembic)
16-Jun-26 | Day 2 | Authentication System | Create user registration, login, JWT authentication, role management, password encryption, forgot password APIs, session management and protected routes. | Complete authentication module |  | Completed
17-Jun-26 | Day 3 | Dashboard Layout | Build dashboard layout, sidebar navigation, header, profile section, campaign statistics cards, responsive design and routing structure. | Dashboard skeleton ready |  | Completed (Dashboard.tsx exists)
18-Jun-26 | Day 4 | Database Architecture | Design tables for Users, Leads, Campaigns, Calls, Agents, Analytics, Recordings and Transcripts. Create database relationships and migrations. | Database schema completed |  | Partially Done (Using MongoDB, schema not strictly defined via Alembic)
19-Jun-26 | Day 5 | Industry Module | Create industry selection page where users can choose AI, Healthcare, Education, SaaS, Real Estate, Manufacturing etc. Save selected industries for campaign personalization. | Industry management module |  | Partially Done
20-Jun-26 | Day 6 | Natural Language Search UI | Build search interface where user can type queries like "Find 100 AI founders with 50+ employees in India". Add search history and filters. | Lead discovery UI |  | Not Started
22-Jun-26 | Day 7 | Query Understanding Engine | Create AI-powered query parser that converts natural language into structured filters such as industry, designation, employee count, location and company size. | Query parser service |  | Not Started
23-Jun-26 | Day 8 | Apollo Integration Setup | Integrate Apollo API, create authentication flow, search APIs and lead fetching services. | Apollo integration working |  | Completed
24-Jun-26 | Day 9 | Apollo Lead Extraction | Extract name, company, designation, LinkedIn profile, email and company details from Apollo results. | Lead extraction pipeline |  | Partially Done
25-Jun-26 | Day 10 | Hunter Integration | Integrate Hunter API for email discovery and company contact enrichment. | Hunter enrichment module |  | Not Started
26-Jun-26 | Day 11 | Google Maps Integration | Integrate Google Places API and create search functionality for local businesses. Collect business name, phone number, website and address. | Maps search engine |  | Not Started
27-Jun-26 | Day 12 | Website Scraper Development | Build website crawler to extract phone numbers, emails, social links and contact information from company websites. | Scraping engine |  | Not Started
29-Jun-26 | Day 13 | Data Enrichment Engine | Combine data from Apollo, Hunter, Google Maps and website scraping into a single lead profile. | Lead enrichment service |  | Not Started
30-Jun-26 | Day 14 | Lead Verification Engine | Remove duplicate leads, validate phone numbers and emails, score lead quality and identify missing information. | Lead verification system |  | Not Started
1-Jul-26 | Day 15 | Lead Storage System | Store all discovered leads in database with filtering, searching, tagging and export functionality. | Lead management module |  | Partially Done (Using MongoDB, schema not strictly defined via Alembic)
2-Jul-26 | Day 16 | Agent Marketplace UI | Create page displaying all available agents such as Product Promotion, Event Promotion, Follow-up, Customer Engagement and Deal Closing agents. | Agent marketplace |  | Not Started
3-Jul-26 | Day 17 | Product Promotion Agent | Create configuration form where users enter product details, benefits, offer details and CTA. | Product Promotion Agent |  | Not Started
4-Jul-26 | Day 18 | Event Promotion Agent | Create event details form with event name, location, date, audience and registration details. | Event Promotion Agent |  | Not Started
6-Jul-26 | Day 19 | Follow-up & Engagement Agents | Create templates for customer engagement, follow-up campaigns and relationship-building calls. | Follow-up Agent |  | Not Started (No Vapi integration found)
7-Jul-26 | Day 20 | Deal Closing Agent | Create closing-focused workflow with objection handling, pricing discussion and conversion logic. | Deal Closing Agent |  | Not Started
8-Jul-26 | Day 21 | Prompt Generator Engine | Generate optimized prompts based on selected agent, campaign objective, industry and user inputs. | Prompt generation service |  | Partially Done
9-Jul-26 | Day 22 | Script Generation Engine | Generate complete call scripts including introduction, discovery questions, objection handling, CTA and closing. | Script generation module |  | Not Started
10-Jul-26 | Day 23 | Script Editor | Allow users to review, edit and save generated scripts before launching campaigns. | Script editor |  | Partially Done
11-Jul-26 | Day 24 | Voice Selection System | Allow users to choose voice type, gender, language, accent and speaking style. | Voice configuration module |  | Not Started
13-Jul-26 | Day 25 | Campaign Builder | Combine lead list, agent type, prompt and script into campaign creation workflow. | Campaign builder |  | Partially Done
14-Jul-26 | Day 26 | Calling Queue Manager | Create queue management system for handling thousands of calls without overloading APIs. | Queue management |  | Not Started
15-Jul-26 | Day 27 | Calling Agent Integration | Connect generated campaigns to existing AI calling infrastructure. | Calling integration |  | Not Started (No Vapi integration found)
16-Jul-26 | Day 28 | Call Scheduling System | Allow immediate calling or scheduled calling at specified times. | Scheduler module |  | Not Started
17-Jul-26 | Day 29 | Call Recording Storage | Store all call recordings securely with campaign mapping. | Recording system |  | Not Started (No Vapi integration found)
18-Jul-26 | Day 30 | Transcript Processing | Generate and store transcripts from completed calls. | Transcript module |  | Not Started
20-Jul-26 | Day 31 | CRM Module | Create lead status tracking, campaign history, follow-up actions and communication timeline. | CRM system |  | Partially Done
21-Jul-26 | Day 32 | Lead Status Automation | Automatically classify leads as Interested, Not Interested, Callback, Meeting Booked or Closed. | Lead classification |  | Not Started
22-Jul-26 | Day 33 | Analytics Dashboard | Display call statistics, conversion rates, campaign performance and lead outcomes. | Analytics dashboard |  | Not Started (No Vapi integration found)
23-Jul-26 | Day 34 | Reporting Module | Generate downloadable reports in PDF and Excel formats. | Reporting system |  | Not Started
24-Jul-26 | Day 35 | Notifications System | Notify users about completed campaigns, booked meetings and important events. | Notification system |  | Partially Done
25-Jul-26 | Day 36 | Admin Panel | Manage users, campaigns, API keys, subscriptions and system monitoring. | Admin dashboard |  | Partially Done
27-Jul-26 | Day 37 | Security Implementation | Implement API security, rate limiting, role permissions and audit logging. | Security layer |  | Not Started
28-Jul-26 | Day 38 | Testing & Bug Fixes | Perform end-to-end testing for all modules and resolve issues. | QA report |  | Not Started
29-Jul-26 | Day 39 | Production Deployment | Deploy frontend, backend, database and monitoring tools to production. | Live deployment |  | Partially Done (Using MongoDB, schema not strictly defined via Alembic)
30-Jul-26 | Day 40 | Documentation & Handover | Prepare technical documentation, API documentation and deployment guides. | Complete documentation |  | Not Started